Instructions for use of the ESFRLP Model Procurement/Disbursement Policy-2024 Cycle

1. The yellow highlighting in the document is used by NCHFA to show specific reference items which must be reviewed and likely revised. The blue highlighting in the document is used to show model language for optional practices. The green highlighting is used to show revised language in the ESFRLP24 cycle.

2. To facilitate reduced NCHFA approval times for content changes your organization makes to the policy, use green or other color highlighting to show changes to your organization’s assigned NCHFA case manager.

3. Date submitted: _______________________________________________________

4. Person for NCHFA to contact concerning revisions: __________________________

5. Provide any notes to your NCHFA case manager below:

__________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

6. When adopting this policy:

- Please review to ensure that the policy mirrors the way that your organization functions.

- Change all personnel, location, income and date references as needed, at minimum, and delete all highlighting.

- Once all adjustments are made and your NCHFA case manager has approved your ESFRLP Policy, delete this page prior to adoption.

Last updated: 7/17/2024

Last Updated: 4/23/2019

City of Dunham

Procurement and Disbursement Policy

For the 2024 Cycle of the

### ESSENTIAL SINGLE-FAMILY REHABILITATION LOAN POOL

## PROCUREMENT POLICY

- To the maximum extent practical, the City of Dunham (the City) promotes a fair, open and competitive procurement process as required under the North Carolina Housing Finance Agency’s (NCHFA) Essential Single-Family Rehabilitation Loan Pool (ESFRLP). Bids are invited from Contractors who are part of the City’s approved contractor registry. Any current contractor listed with and approved by the City and in good standing (ie. no unresolved past performance issues and not listed on the federal or state debarred list) will receive automatic approval status on the Approved Contractor Registry.

- To be listed in the Approved Contractor Registry, a contractor must complete an application, have their recent work inspected, reviewed and approved by the City’s Rehabilitation Specialist and submit proof of insurance.

(Option) Describe the process to qualify (describing eligible characteristics) or disqualify contractors from bidding. (provide language) Qualified vendors are those substantially meeting the applicable specifications and laws, taking into consideration quality, performance and the time specified in the bids for performance of the contract. Contact the City for an application to become a qualified vendor.

- At least three eligible contractors on the City’s Approved Contractor Registry shall be invited to bid on each job and the lowest responsive and responsible bidder shall be selected for the contract.  “Responsive and responsible” means (a) the contractor is deemed able to complete the work in a timely fashion, (b) the bid is within 15%, in either direction, of the City’s cost estimate, (c) the contractor has not been suspended or debarred and (d) there is no conflict of interest (real or apparent).

(Option) Describe the process and requirements used to notify contractors of projects available for bidding. (provide language) The City will conduct a public or virtual (describe the medium like ‘via Zoom’) bid allowing qualified vendors to provide quotes, bids or proposals for the product or services needed. Every reasonable effort will be made to receive at least three quotes, bids or proposals.

All contractors working on pre-1978 units must be Renovation, Repair and Painting Rule (RR&P) Certified Renovators working for Certified Renovation firms; only those contractors with both firm certificate and the qualified renovator’s letter on file will be invited to bid on pre-1978 homes.  For units where abatement is required or with more than $25,000 of construction costs not attributed to Lead-Based Paint (LBP) stabilization/removal, projects must use a certified lead abatement firm as required by North Carolina’s Lead Hazard Management Program for Abatement Activities (LHMP).  Both firm types are listed at this website: https://schs.dph.ncdhhs.gov/lead/accredited.cfm.

- Although bid packages may be bundled for multiple job sites, the bids for multiple job sites shall be considered separate and apart when awarded and shall be awarded to the lowest responsive and responsible bidder(s) for each job site.

- Bid packages shall consist of an invitation to bid, work write up(s) and bid sheet(s) for each job, including instructions for distribution and receipt of bids. Contractors will be given no less than seven days in which to inspect the property and prepare bid proposals. Each contractor will need access to all parts of the house in order to prepare a bid. A bid opening will be conducted in the Commissioner’s Board Room located at the Kucab County Court House, 111 Main Street, Dunham, NC at a specified date and time, with all bidders invited to attend.

- Bids must include a cost-per-item breakdown with line item totals equaling the submitted bid price. Discrepancies must be reconciled prior to a contract being awarded.

- The City reserves the right to reject any or all bids at any time during the procurement process.

- In the event of a true emergency situation, the City reserves the right to waive normal procurement procedures in favor of more expedient methods, which may include seeking telephone quotes, electronic bids and the like. Should such methods ever become necessary the transaction will be fully documented. In the event phone bids are used, the City of Dunham will call the first three responsive contractors on the Approved Contractor Registry who have indicated a desire to be on the telephone call list. The City will track who has been called and responsive, and will rotate through the full list before beginning the rotation again.

- All sealed bids will be opened publicly at a time and place to be announced in the bid invitation. All bidders are welcome to attend. Within 72 hours of the bid opening, after review of bid breakdowns and construction schedules, the winning bidders will be selected. All bidders and the homeowner will be notified in writing of 1) the selection of the winning bid, 2) the amount of the winning bid, 3) the amount of the City’s cost estimate, and 4) the specific reasons for the selection, if other than the lowest bidder was selected.

- The contractor is responsible for obtaining a building permit for the project before beginning work if supported by the local jurisdiction. The permit must be posted at the house during the entire period of construction. If applicable, the contractor will obtain a permit for lead hazard related activities. City of Dunham ESFRLP staff will closely monitor the contractor during the construction period to make sure that the work is being completed according to the work write-up (which is made a part of the rehabilitation contract by reference) and in a timely fashion. Local Code Enforcement Officials will inspect the work for compliance with the NC State Building Code and the local minimum housing code, when applicable. To protect personal property the homeowner will be responsible for working with the contractor toward clearing work areas of personal property as needed as much as practicable. The contractor will be responsible for all clearing and cleaning activities necessary due to construction activities.

- Any change to the original scope of work must be reduced to writing in the form of a change order to be agreed upon and signed by all parties to the original contract including at minimum, the homeowner, the contractor and two representatives of the City. The change order must also detail any changes to the original contract price and completion date.

- No work may begin prior to a contract being awarded and executed and a written order to proceed provided to the contractor. In addition, a pre-construction conference and “walk thru” shall be held at the work site prior to commencement of repair work. At this time, the homeowner, contractor and ESFRLP City of Dunham program representatives will discuss the details of the work to be completed. Starting and ending dates will be finalized, along with any special arrangements such as weekend or evening work hours and disposition of items to be removed from the home. Within 24 hours of the pre-

construction conference, the City of Dunham will issue a "proceed order" formally instructing the contractor to commence work by the agreed-upon date.

- The City of Dunham is an equal opportunity employer, implements non-discriminatory practices in its procurement/disbursement and will make special outreach efforts to include M/WBE (Minority/Women Business Enterprise) businesses within its contractor and subcontractor pool. Contractors will be chosen by the above criteria without regard to race, color, religion, national origin, age, sex, familial status and/or disability.

DISBURSEMENT POLICY

- All repair work must be inspected by (a) the City’s Rehabilitation Specialist, (b) the local building or minimum housing code inspector when applicable and (c) the homeowner prior to any payments to contractors. If all work is deemed satisfactory and all other factors and written agreements are in order, payment shall be issued upon presentation of an original invoice from the contractor. Contractor should allow 21 business days for processing of the invoice for payment.

- The contractor is entitled to request two partial payments and a final payment. The first partial payment may be requested when the work is 50% complete. The second partial payment may be requested when the work is 85% complete. When a payment is requested, the Rehabilitation Specialist will inspect the work within three days, determine percentage of job completion and calculate a payment based on 90% of the total work completed.

- Following construction, the contractor and the Rehabilitation Specialist will meet with the Homeowner in a post-construction conference. At this conference the contractor will hand over all owner's manuals and warranties on equipment and products to the homeowner and be available to answer homeowner questions.

- Project Closeout: When the contractor declares the work complete, the Rehabilitation Specialist will thoroughly inspect the work. If any of the work is deemed unsatisfactory, it must be corrected prior to authorization of final payment. If the contractor fails to correct the work to the satisfaction of the City’s Rehabilitation Specialist, payment may be withheld until the work is deemed satisfactory. (Contractors may follow the City’s Essential Single-Family Rehabilitation Loan Pool Assistance Policy if a dispute occurs; however, contractors shall abide by the final decision as stated in the policy). The Homeowner, Project Administrator and Rehabilitation Specialist will sign off on the work. After receipt of the contractor's final invoice, inspections, certificate of completion and lien releases, the final payment will be ordered. All material and workmanship will be guaranteed by the contractor for a period of one-year, using the date the Rehabilitation Specialist declares all work complete and approves the final invoice for payment, the homeowner will be provided the one-year warranty date in writing.

- The City assures, through this policy, that adequate funds shall be available to pay the contractor for satisfactory work.

- All contractors, sub-contractors and suppliers must sign a lien waiver prior to disbursement of funds.

The Procurement and Disbursement Policies are adopted this the ________ day of ___________________20___.

City of Dunham

BY: 	________________________________________________________

ATTEST:	________________________________________________________

CONTRACTORS STATEMENT:

I have read and understand the attached City of Dunham Procurement and Disbursement Policy.

BY:		________________________________________________________

COMPANY NAME:	______________________________________________

WITNESS:		______________________________________________